## GanttChart
[Project Name] Project Schedule | [9 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
|  | Project Start Date | 2024-02-14 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
|  | Project Lead | [7 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15
 | time axis 2024-02-12 to 2024-04-21
WBS |  | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-02-12 to 2024-04-21
1 | 15 | Pw Skills |  |  |  | - |  |  | - | bar: 2024-02-19 to 2024-02-20
1.1 | 35 | HTML | [Name] |  | 2018-01-29 | 2018-02-02 | 5 | 100% | 5 | bar: 2024-02-19 to 2024-02-20
1.1.1 | 44 | Video - Media Forms, Modren Html, seo | bar: 2024-02-19 to 2024-02-20
1.2 | 35 | CSS | bar: 2024-02-20
1.2.1 | 44 | Video - css Basics | bar: 2024-02-20
1.3 | 35 | JS
2 | 15 | Practice Projects Youtube |  |  |  | - |  |  | - | bar: 2024-02-19
2.1 | 35 | Youtube Clone JS Mastery |  |  | 2018-02-10 | 2018-02-13 | 4 | 0% | 2 | bar: 2024-02-19
2.1.1 | 44 | Practice - Navbar basic setup | bar: 2024-02-19
2.1.2 | 44 | Practice - SideBar basic Setup | bar: 2024-02-19
3 | 15 | Theory Youtube videos |  |  |  | - |  |  | - | bar: 2024-02-19 to 2024-02-20
3.1 | 35 | Theory AI | bar: 2024-02-19 to 2024-02-20
3.1.1 | 44 | Generative AI in a Nutshell - how to survive and thrive in the age of AI |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-19 to 2024-02-20
3.2 | 35 | Theory Life |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
3.2.1 | 44 | How the Way You Respond to Boredom Changes Your Life |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
3.3 | 35 | Theory WebDev |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
3.3.1 | 44 | How to Master React in 2024 - The React Roadmap |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
3.4 | 35 | Theory Job |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
3.4.1 | 44 | These Mistakes Can End Your Career As A Software Developer! |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
3.5 | 35 | Theory Deployment |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
3.5.1 | 44 | Docker in 100 Seconds |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1 | bar: 2024-02-20
4 | 15 | [Task Category] |  |  |  | - |  |  | -
4.1 | 35 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
5 | 15 | [Task Category] |  |  |  | - |  |  | -
5.1 | 35 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
6 | 15 | [Task Category] |  |  |  | - |  |  | -
6.1 | 35 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
7 | 15 | [Task Category] |  |  |  | - |  |  | -
7.1 | 35 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
8 | 15 | [Task Category] |  |  |  | - |  |  | -
8.1 | 35 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
9 | 15 | [ Level 1 Task or Phase ] Example |  |  |  | - |  |  | -
9.1 | 35 | . [ Level 2 Task ] Example |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
9.1.1 | 44 | . . [ Level 3 Task ] Example |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
9.1.1.1 | 54 | . . . [ Level 4 Task ] Example |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
Video |  | Video -
Practice |  | Practice -
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 |  | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 |  | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 |  | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 |  | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
Note on A5: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C5: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D5: Task Lead Enter the name of the Task Lead in this column.
Note on E5: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F5: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G5: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H5: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I5: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J5: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.